## 2024-2025 Work Plan
|  | CCFSA Work | Plan 2026
1. Capacity Building and Networking: Ensure our presence is known, expand network, and support partners.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline | Status
a. Increase our following on existing social media sites. | 1) Reach out to other organizations and send friend requests 2) Establish a work group to form a strategy for CCFSA social media accounts and best practices for operation | 1) Project Coordinator 2) Lisa, Shannon | 1) Review at each CCFSA Leadership Team meeting 2) Initial meeting was held on 9/15/2026. A meeting summary, a list of action items and questions to be discussed were created. | 1) Posting once/week Jan 1 - Oct 25: Facebook: +37 followers (+19%) LinkedIn: +18 Followers (26%) 2) Lisa and Shannon host the social media subcommittee meetings and report the dicussion results at each Leadership Team meeting
b. Keep the website up to date and make sure it is easy to find information. | 1) Explore and maintain current content | 1) Project Coordinator and Center for Land Use and Sustainability | 1) Ongoing, and as needed, review monthly | Migration to ship.edu and review were completed; 3 website hosting providers have been identified, with preliminary quotes on content migration + hosting;
c. Participate in meetings and events hosted by partners to promote CCFSA. | Ongoing meetings: Adams County Food Policy Council, FSLN, Healthy Franklin County, PA Food Policy Council, PHAC, SCRC, SMP, SPO, PCFAC, SHSC, DCFAC Short-term meetings: 1) 2026 Food As Medicine in Community Forum | Project Coordinator and Leadership Team members, short-term meetings listed are open to everyone | Ongoing meetings: varying schedules Short-term meetings: 1) Dec 3 & 4 | Ongoing Meetings: PCFAC monthly meetings (11/10, 12/8, 1/12, 2/9...) 2pm on Tuesdays; DCFPC quarterly meetings; SCRC Human Service Council Meetings Short-term meetings: FAM Community Forum: Dec 3 1-4pm, Dec 4 7:30am to 3:30pm
d. Offer educational sessions that are responsive to emerging trends and have targeted outcomes. | 1) Fall 2026 Community Conversation "Building Better Plates: Practical Nutrition for Real Life" 2) Spring 2027 Community Conversation | 1) Katie, Lisa and Xin 2) Heather, Steph, Kelton, Xin | 1) Thursday, September 24, 6-7:30 pm,Project SHARE HQ 2) Topic: Climate change and projected impacts in the region; tentative format: a mix of student research presentations and expert keynote speeches/panels | 1) Completed; a recap will be included in the CCFSA winter newsletter 2) For farmers, fruit growers, agriculture service providers and organizations.
e. Explore feasibility of CCFSA hosting the 2027 Regional Food Systems Gathering, usually in June. | 1) Resume the conversation with Adams County and others in Spring 2027 | 1) Need a Champion | 1) Late fall 2026 or early spring 2027-discuss with Leadership Team and seek funding | Revisit the topic during the Dec 2 Leadership Team meeting?
2. Assist in SNAP/WIC Promotion: Increase awareness of and participation in supplemental food programs.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline | Status
a. Increase enrollment in SNAP/WIC. | 1) Contact local enrollment providers, determine what support is needed, enrollment changes, etc. 2) Advocate for a simplified enrollment process 3) Participate in SNAP Blitz with CPFB (Zach Zook, lead) | 1) Project Coordinator 2) Support the work of PHAC, The Food Trust, and others 3) Need a Champion | 1) Ongoing, review quarterly 2) As needed 3) Spring 2026, if CPFB has availability. Suggested April or May to Zach Zook | 1) Basic computer skills 2) Signed on a letter of support circulated by FRAC to support the full funding of WIC 3) Project was attempted and discontinued in 2026 (?)
b. Leverage federal and state resources to help local offices. | 1) Participate in PA Food Policy Council meetings to identify opportunities 2) Work with the Pennsylvania Hunger Action Coalition (PHAC) | 1) Project Coordinator and other Leadership Team members 2) Project Coordinator, Gail Witwer, and other Leadership Team members | 1) Ongoing, meetings 4 times a year, 1 per quarter 2) Ongoing, meetings 2 times a year, 1 in Spring and 1 in Fall | 1) 2026 PA-FPC Meetings: 03/27/26 2-4 pm 06/18/26 1-3 pm 09/10/26 1-3 pm 12/04/26 2-4 pm 2)PHAC:
3. Advocate for Child Focused Feeding Programs: Ensure the basic food needs of all children are met.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline | Status
a. Advocate for feeding programs partnered with the schools to provide children with food before, during, and after school hours. | 1) Support universal free school breakfast and lunch in Pennsylvania schools 2) Participate in policy coalition activities and advocacy days with policy coalitions. | 1) Work with CPFB, PHAC, FRAC and other organizations. 2) Katie Kerr | 1) Ongoing, and as needed, review quarterly 2) Ongoing, report at each Leadership Team meeting | 1) Universal School Lunch is included in CCFSA Advocacy One-Pager 2) The CCFSA Advocacy One-Pager is in the final editing stage. The next step is to have it reviewed by the external consultant hired by the Parternship.
b. Promote and advocate for school backpack programs, school food pantries, and summer feeding programs. | 1) Highlight successful programs on social media 2) Participate in local events | 1) Project Coordinator 2) Leadership Team members | 1) Ongoing, review quarterly 2) Ongoing, as needed, report at each Leadership Team meeting | 1)Included Summer Food Access for Children Programs in the spring newslette and continuously promote these programs on social media throughout the year 2) Updates from the leadership team/guest
c. Advocate for Farm to School Initiatives. | 1) Reach out to local School Districts (School Boards, Wellness Committees) to encourage purchase of local foods 2) Sign on to relevant letters of support | 1) CCFSA Leadership Team members will include them in relevant meetings and outreach 2) Project Coordinator will continue to sign-on to advocacy letters | 1) Begin in Spring 2026 2) Ongoing, as needed, review at each Leadership Team meeting | 1) 2)
d. Advocate to increase meal participation rates in schools | 1) Reach out to local School Districts to promote awareness of the county's below-state-average meal participation rates 2) Provide information/education on how to increase the school average daily meal participation rate at appropriote occasions | 1) Leadership Team Members 2) Leadership Team Members | 1) Ongoing 2) Ongoing | 1) Katie and Shannon had a meeting with CVSD food service director with regards to this issue at the end of spring. No updates yet. 2) Xin established a connection with the social work/human service network in the Shippensburg Area School District. Ready to make connections if the team wishes to continue pursuing progress on this topic.
4. Increase Accessibility of Local Food Banks and Pantries: Ensure fair and equitable access to healthy and nourshing foods for those in need.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline | Status
a. Identify and direct resources to vulnerable, underserved communities in Cumberland County. | 1) Continue to maintain food pantry calendar (online) and printable PDF link 2) Explore access for those who lack transportation | 1) Project Coordinator 2) Possible work group to explore expanded food pantry hours, creating a carpool list, and/or partner with other providers like Door Dash or Rabbit Transit | 1) Formally, two times each year, December 31 and July 1, and as needed 2) TBD | 1) Reviewed and updated on Oct 27. 2) Decided to table this idea at the December 2025 CCFSA Leadership Team meeting
b. Provide education for those utilizing The Emergency Food Assistance Program (TEFAP) to maximize their food dollars. TEFAP is a federal program that helps supplement the diets of people with low income by providing them with emergency food assistance at no cost. | 1) Highlight initiatives on CCFSA social media 2) Promote Project SHARE & SPO cooking classes/videos in newsletter and on social media | 1) Project Coordinator 2) Project Coordinator | 1) At least once a month, if news is relevant 2) Twice a year in newsletter (Spring and Fall) and on social media as opportunities arise | 1) The Healthy Food Pantry Initiative needs reevaluation. Project Pending. 2) Will be included the the Winter 2026 Newsletter
c. Coordinate among grassroot organizations who provide food release to the community with established food pantries, to reduce safety risks for everyone and increase efficiency of resources | 1) Gather information on projected risks and guidelines for "blessing boxes" and similar charity actions; 2) Assist to organize a forum for a small number of stakeholders, with faciliation support from Diana Russell's team at Institute of Conservation Leadership | 1) Gail Witwer 2) Gail Witwer, Project Coordinator | 1) By the Oct 7 Leadership Team meeting 2) Estimated to be early 2027 | Waiting on Diana's team's availability
5. Promote Agriculture in the County: Advocate for farmland preservation to ensure local farms and farmers are part of the food system.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline | Status
a. Advocate for continued investment in the farmland preservation program. | 1) Write letter of support to the commissioners | 1) Project Coordinator assists Stephanie Williams, Cumberland County Senior Planner. | 1) At least once a year, send a formal letter to the Commissioners | 1) Last support letter sent 10/15/26
b. Support opportunities for agriculture education. | 1) Support local 4H, FFA, PASA, and Farm Bureau to advocate for ag education in schools | 1) Explore opportunities with Penn State Extension, Cumberland County Planning Office and others. | 1) As opportunities arise
c. Support and promote the purchase of local farm products through farmers markets, farm stands, and CSAs. | 1) Support an update of the Cumberland County Local Food Guide | 1) Stephanie Williams and Visitor's Association with the assistance of the Project Coordinator. | 1) 2026 goal, explore possibility of using a student at Dickinson or Shippensburg undergraduate or graduate student. | 1) Possible option for a spring 2027 internship project
d. Support and advocate for the expansion of EBT usage with farmers markets, farm stands, and CSAs. | 1) Research farmers markets, farm stands, and CSAs that accept EBT | 1) CPFB can provide annual USDA data to determine next steps. | 1) 2026 goal, initial meeting with Erik Smith (FOTS Manager) and Lisa Maddux (Project SHARE) TBD | Provided tools to locate benefit-accepting farmers' markets and farmstands in the county in CCFSA Spring Newsletter
6. Achieve long-term financial stability for CCFSA.
Priorities for 2026 Work Plan | Action/Tasks | Identified Champion | Timeline
a. Seek out and pursue grants and other funding sources. | 1) Continue to explore grants 2) Renew Partnership for Better Health grant (2027) | 1) Heather Plumridge, Lisa Maddux 2) CLUS and Partnership For Better Health | 1) Ongoing, as opportunities arise 2) Fall 2026, by December 1st, if this grant will be pursued | 1) Update from Lisa and Heather 2) Grant is not renewed with SU/CLUS. CCFSA will be brought back in Partnership for Better Health and coordinated by Kelton Artuson
b. Pursue Shippensburg University Foundation support in partnership with CLUS. The ultimate goal is for CCFSA to be sulf-sustaining. | 1) Holly Smith reached out to Amanda Shaeffer, SU Foundation (September 2025). Continue to have conversations | 1) Nathan Thomas (CLUS acting Director) with the support of the Project Coordinator | 1) Continue to work on this idea throughout 2026 and beyond | 1) In May, Xin and Nathan met with Liz Fisher and picked her brain about obtaining grants through the ShipU foundation and the grant office. 2) Most of SU foundation grants focus on the goal of benefiting SU students